## Sheet1
[6 empty] | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
project | work | estimate man days | actual man days | done | who | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-09-04 | 2017-09-11 | 2017-09-18 | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25
[9 empty] | kick-off | spec rev | [10 empty] | demo conc 0 |  |  | start Concept1 |  |  |  | concept1 module | [7 empty] | end Concept1
[6 empty] | 8 | 8 | 3.5 | 7 | 5 | 6 | 2 | 4 | 6 | 5 | 7 | 0 | 0 | 1 | 0 | 4 | 2.6 | 1.8 | 3.9 | 3.9 | 5.9 | 4.6 | 4.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 4.3 | 6.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3
LE_NB_IOT_CONTROLLER concept0 | analyze current sensor | 1 | 4 | y | jrh | 2017-05-01: 4
LE_NB_IOT_CONTROLLER concept0 | test current sensor | 1 | 4 | y | jrh | 2017-05-01: 4
LE_NB_IOT_CONTROLLER concept0 | analyze current meas and comm | 1 | 3 | y | jrh | 2017-05-08: 3
LE_NB_IOT_CONTROLLER concept0 | test current system | 1 | 5 | y | jrh | 2017-05-08: 5
LE_NB_IOT_CONTROLLER concept0 | specification sensor | 5 | 5 | y | jrh | 2017-05-15: 3; 2017-06-05: 2
LE_NB_IOT_CONTROLLER concept0 | design sensor | 10 | 8 | y | jrh | 2017-05-22: 4; 2017-06-12: 2; 2017-06-19: 2
LE_NB_IOT_CONTROLLER concept0 | test sensor | 0 | 0 |  | jrh
LE_NB_IOT_CONTROLLER concept0 | layout sensor | 0 | 0 |  | jrh
LE_NB_IOT_CONTROLLER concept0 | production sensor | 0 | 0 |  | jrh
LE_NB_IOT_CONTROLLER concept0 | certification sensor | 0 | 0 |  | jrh
LE_NB_IOT_CONTROLLER concept0 | installation and test sensor | 0 | 0 |  | jrh
LE_NB_IOT_CONTROLLER concept0 | specification radio | 10 | 13 | y | jrh | 2017-05-22: 3; 2017-05-29: 5; 2017-06-05: 4; 2017-06-26: 1
LE_NB_IOT_CONTROLLER concept0 | design radio | 30 | 19 | n | jrh | 2017-06-19: 2; 2017-06-26: 5; 2017-07-03: 5; 2017-07-10: 7; 2017-07-17: vacation; 2017-07-24: vacation
LE_NB_IOT_CONTROLLER concept0 | test radio | 0 | 1 | y | jrh | bar: 2017-07-31
LE_NB_IOT_CONTROLLER concept0 | layout radio | 0 | 0 |  | jrh
LE_NB_IOT_CONTROLLER concept0 | production radio | 0 | 0 |  | jrh
LE_NB_IOT_CONTROLLER concept0 | certification radio | 0 | 0 |  | jrh
LE_NB_IOT_CONTROLLER concept0 | installation and test radio | 0 | 0 |  | jrh
LE_NB_IOT_CONTROLLER concept0 | documentation | 5 | 2 | y | jrh | 2017-08-14: 2
LE_NB_IOT_CONTROLLER concept0 | TOT SUM | 64 | 64
LE_NB_IOT_CONTROLLER concept0 | TOT SUM HOURS | 480 | 480
LE_MICRO | analyze, maintenance, development | 10 | 9.5 |  | jrh | 2017-08-21: 0.5; 2017-08-28: 0.5; 2017-09-04: 0.5; 2017-09-11: 0.5; 2017-09-18: 0.5; 2017-09-25: 0.5; 2017-10-02: 0.5; 2017-10-09: 0.5; 2017-10-16: 0.5; 2017-10-23: 0.5; 2017-10-30: 0.5; 2017-11-06: 0.5; 2017-11-13: 0.5; 2017-11-20: 0.5; 2017-11-27: 0.5; 2017-12-04: 0.5; 2017-12-11: 0.5; 2017-12-18: 0.5; 2017-12-25: 0.5
LE_AMEKA | feasibility | 4 | 3.2 |  | jrh | 2017-05-15: 0.5; 2017-08-21: 0.8; 2017-08-28: 1; 2017-09-04: 0.3; 2017-09-11: 0.3; 2017-09-18: 0.3
LE_AMEKA | Installation | 1 | 0.9 |  | jgs | 2017-08-21: 0.3; 2017-08-28: 0.3; 2017-09-04: 0.3
LE_AMEKA | Linsight | 1 | 0.9 |  | ehh | 2017-09-11: 0.3; 2017-09-18: 0.3; 2017-09-25: 0.3
LE_AMEKA | TOT SUM | 6 | 5
LE_AMEKA | TOT SUM HOURS | 45 | 37.5
HeiRobot! | [5 empty] | 2017-08-14: 1; 2017-08-21: 1; 2017-08-28: 0; 2017-09-04: 1.8; 2017-09-11: 1.8; 2017-09-18: 1.8; 2017-09-25: 1.8; 2017-10-02: 1.8; 2017-10-09: 1.8; 2017-10-16: 1.8; 2017-10-23: 1.8; 2017-10-30: 1.8; 2017-11-06: 1.8; 2017-11-13: 1.8; 2017-11-20: 1.8; 2017-11-27: 1.8; 2017-12-04: 1.8; 2017-12-11: 1.8; 2017-12-18: 1.8; 2017-12-25: 1.8
Digital Twin | bar: 2017-08-14
LE_NB_IOT_CONTROLLER concept1 | specification sensor | 1 | 1 |  | jrh | bar: 2017-09-04
LE_NB_IOT_CONTROLLER concept1 | design sensor | 5 | 5 |  | jrh | 2017-09-11: 1; 2017-09-18: 3; 2017-09-25: 1
LE_NB_IOT_CONTROLLER concept1 | test sensor | 1 | 1 |  | jrh | bar: 2017-09-25
LE_NB_IOT_CONTROLLER concept1 | layout sensor | 0 | 0
LE_NB_IOT_CONTROLLER concept1 | production sensor | 0 | 0
LE_NB_IOT_CONTROLLER concept1 | certification sensor | 0 | 0
LE_NB_IOT_CONTROLLER concept1 | specification radio | 2 | 2 |  | jrh | 2017-10-02: 2
LE_NB_IOT_CONTROLLER concept1 | design radio | 18 | 15 |  | jrh | 2017-10-09: 3; 2017-10-16: 3; 2017-10-23: 3; 2017-10-30: 3; 2017-11-06: 3
LE_NB_IOT_CONTROLLER concept1 | test radio | 3 | 2 |  | jrh | 2017-11-13: 2
LE_NB_IOT_CONTROLLER concept1 | layout radio | 0 | 0
LE_NB_IOT_CONTROLLER concept1 | production radio | 0 | 0
LE_NB_IOT_CONTROLLER concept1 | certification radio | 0 | 0
LE_NB_IOT_CONTROLLER concept1 | installation and test radio | 2 | 2 |  | jrh | 2017-11-20: 2
LE_NB_IOT_CONTROLLER concept1 | documentation (including server work) | 2 | 2 |  | ehh, jrh | 2017-11-20: 2
LE_NB_IOT_CONTROLLER concept1 | TOT SUM | 34 | 30
LE_NB_IOT_CONTROLLER concept1 | TOT SUM HOURS | 255 | 225
LE_NB_IOT_CONTROLLER concept2 | specification sensor | 2 | 0
LE_NB_IOT_CONTROLLER concept2 | design sensor | 5 | 0
LE_NB_IOT_CONTROLLER concept2 | test sensor | 1 | 0
LE_NB_IOT_CONTROLLER concept2 | layout sensor | 2 | 0
LE_NB_IOT_CONTROLLER concept2 | production sensor | 0 | 0
LE_NB_IOT_CONTROLLER concept2 | certification sensor | 0 | 0
LE_NB_IOT_CONTROLLER concept2 | specification radio | 3 | 0
LE_NB_IOT_CONTROLLER concept2 | design radio | 34 | 0
LE_NB_IOT_CONTROLLER concept2 | test radio | 3 | 0
LE_NB_IOT_CONTROLLER concept2 | layout radio | 2 | 0
LE_NB_IOT_CONTROLLER concept2 | Incapsulation engineering | 5 | 0
LE_NB_IOT_CONTROLLER concept2 | Incapsulation production | 5 | 0
LE_NB_IOT_CONTROLLER concept2 | production radio | 5 | 0
LE_NB_IOT_CONTROLLER concept2 | certification radio | 5 | 0
LE_NB_IOT_CONTROLLER concept2 | installation and test radio | 2 | 0
LE_NB_IOT_CONTROLLER concept2 | documentation (including server work) | 5 | 0
LE_NB_IOT_CONTROLLER concept2 | TOT SUM | 79 | 0
LE_NB_IOT_CONTROLLER concept2 | TOT SUM HOURS | 592.5 | 0